## ROADMAP
ROADMAP - 2021/2022
Q1 |  |  |  | Q2 |  |  |  |  | Q3 |  |  |  | Q4
July | Aug |  | Sep | Oct | Nov |  | Dec |  | Jan |  | Feb | Mar | Apr |  | May |  | Jun
Website
Current Location Setting | [17 empty] | © Copyright. upGrad Education Pvt. Ltd. All rights reserved
[11 empty] | Dine out Features/ Referals |  |  | Bestseller features |  |  |  | Disclaimer:
| User Sign In/ Sign Up | [16 empty] | All content and material on the upGrad website is copyrighted material, either belonging to upGrad or its bonafide contributors and is purely for the dissemination of education. You are permitted to access print and download extracts from this site purely for your own education only and on the following basis:
[8 empty] | Order Confirmation & Track |  |  |  | Restaurant safety standards/ add on details | [5 empty] | You can download this document from the website for self-use only.
Restaurant Search and Listing | [15 empty] | Advance Booking Features |  | Any copies of this document, in part or full, saved to a disc or to any other storage medium may only be used for subsequent, self-viewing purposes or to print an individual extract or copy for non-commercial personal use only.
[9 empty] | Ratings/time & cost indicators/offers | [8 empty] | Any further dissemination, distribution, reproduction, copying of the content of the document herein or the uploading thereof on other websites or use of the content for any other commercial/unauthorised purposes in any way which could infringe the intellectual property rights of upGrad or its contributors, is strictly prohibited.
|  | Food Listing, Prices and Selection in the restaurant | [15 empty] | No graphics, images or photographs from any accompanying text in this document will be used separately for unauthorised purposes.
[10 empty] | filters add ons |  |  |  | Recommendation features |  |  |  | No material in this document will be modified, adapted or altered in any way.
|  |  | Add to Cart & checkout | [14 empty] | No part of this document or upGrad content may be reproduced or stored in any other web site or included in any public or private electronic retrieval system or service without upGrad’s prior written permission.
[12 empty] | Covid features |  |  | Delivery instructions |  |  | Any rights not expressly granted in these terms are reserved.
Payment Gateways
[7 empty] | Wallet integrations | [5 empty] | Pro Member Features
Mobile
Android V1
iOS V1

## PRODUCT BACKLOG
PRODUCT BACKLOG
S.No | Work Item Type | Work Item Title | Priority (P1, P2 etc) | Comments
1 | F1 | Current Location Setting | P1 | Basic Feature Functionality, Very High Impact
2 | F2 | User Sign In/ Sign Up | P1 | Basic Feature Functionality,Very High Impact
3 | F3 | Restaurant Search and Listing | P1 | Basic Feature Functionality, Very High Impact | © Copyright. upGrad Education Pvt. Ltd. All rights reserved
4 | F4 | Food Listing, Prices and Selection in the restaurant | P1 | Basic Feature Functionality, Very High Impact
5 | F5 | Add to Cart & checkout | P2 | Basic Feature, High Impact | Disclaimer:
6 | F6 | Payment Gateways | P2 | Basic Feature, High Impact | All content and material on the upGrad website is copyrighted material, either belonging to upGrad or its bonafide contributors and is purely for the dissemination of education. You are permitted to access print and download extracts from this site purely for your own education only and on the following basis:
7 | F7 | Order Confirmation & Track | P2 | Basic Feature, High Impact | You can download this document from the website for self-use only.
8 | I1 | Ratings/time & cost indicators/offers | P3 | Add on Feature with High Impact | Any copies of this document, in part or full, saved to a disc or to any other storage medium may only be used for subsequent, self-viewing purposes or to print an individual extract or copy for non-commercial personal use only.
9 | F8 | filters add ons | P3 | Add on Feature with High Impact | Any further dissemination, distribution, reproduction, copying of the content of the document herein or the uploading thereof on other websites or use of the content for any other commercial/unauthorised purposes in any way which could infringe the intellectual property rights of upGrad or its contributors, is strictly prohibited.
10 | I2 | Wallet intergrations | P3 | Add on Feature with High Impact | No graphics, images or photographs from any accompanying text in this document will be used separately for unauthorised purposes.
11 | F9 | Dine out Features/ Referals | P4 | Good to have feature, high impact | No material in this document will be modified, adapted or altered in any way.
12 | I3 | Restaurant safety standards/ add on details | P5 | Good to have feature, low impact | No part of this document or upGrad content may be reproduced or stored in any other web site or included in any public or private electronic retrieval system or service without upGrad’s prior written permission.
13 | I4 | Covid features | P4 | Good to have feature, medium impact | Any rights not expressly granted in these terms are reserved.
14 | I5 | Bestseller features | P4 | Good to have feature, medium impact
15 | I6 | Recommendation features | P4 | Good to have feature, medium impact
16 | F10 | Pro Member Features | P5 | Good to have feature, Low impact
17 | F11 | Advance Booking Features | P5 | Good to have feature, Low impact
18 | I7 | Delivery instructions | P5 | Good to have feature, Low impact

## SPRINT BACKLOG
SPRINT BACKLOG - Sprint 1
S.No | Work Item Type | Work Item Title (User Story) | Related Epic / Feature (if any) | Priority (P1, P2 etc) | Status | Comments
1 | F3 | As a user, I would like to search for restaurants so I can order food from restaurants of my choice | Restaurant Search and Listing | P1 | In Progress | Restaurant searching will be the most basic needed
2 | F3 | As a user, I would like to see a list of restaurants so I can order from any of them | Restaurant Search and Listing | P1 | In Progress | Restaurant listing will be needed to choose from | © Copyright. upGrad Education Pvt. Ltd. All rights reserved
3 | F1 | As a user, I would like the app to pick up my current location using GPS so I can see nearby restaurants | Current Location Setting | P1 | To Do | GPS would be needed to show nearby restaurants who will deliver
Disclaimer:
All content and material on the upGrad website is copyrighted material, either belonging to upGrad or its bonafide contributors and is purely for the dissemination of education. You are permitted to access print and download extracts from this site purely for your own education only and on the following basis:
You can download this document from the website for self-use only.
Any copies of this document, in part or full, saved to a disc or to any other storage medium may only be used for subsequent, self-viewing purposes or to print an individual extract or copy for non-commercial personal use only.
Any further dissemination, distribution, reproduction, copying of the content of the document herein or the uploading thereof on other websites or use of the content for any other commercial/unauthorised purposes in any way which could infringe the intellectual property rights of upGrad or its contributors, is strictly prohibited.
No graphics, images or photographs from any accompanying text in this document will be used separately for unauthorised purposes.
|  | add more rows below if required |  |  |  |  | No material in this document will be modified, adapted or altered in any way.
No part of this document or upGrad content may be reproduced or stored in any other web site or included in any public or private electronic retrieval system or service without upGrad’s prior written permission.
SPRINT BACKLOG - Sprint 2 | [6 empty] | Any rights not expressly granted in these terms are reserved.
S.No | Work Item Type | Work Item Title (User Story) | Related Epic / Feature (if any) | Priority (P1, P2 etc) | Status | Comments
1 | F1 | As a user,I would like to set delivery location so I can change the address as and when needed | Current Location Setting | P1 | To Do | Option to put your current address for delivery
2 | F1 | As a user, I would like the app to save my address so I don't have to enter delivery location everytime I order | Current Location Setting | P1 | To Do | Option to save addresses which any user would want
3 | F1 | As a user, I would like to see the recent location searches so that I can choose that location easily again | Current Location Setting | P1 | To Do | Option to see recent location searches which users would want
4 | F3 | As a user, I would like to see the recently searched restaurants so that I can quickly choose to save time & effort | Restaurant Search and Listing | P1 | To Do | Option to see recent restaurant searches which users would want